## Slide 1: Leading A Group

## Slide 2: Leading a Group
A group needs a leader
  A leader is responsible for making final decisions
  The leader is responsible for assigning tasks
  The leader is responsible for making sure tasks are completed on time
  Sample Tasks
    Designing
    Coding
    Quality Assurance including testing and reviews
    Documentation including Javadocs and UML diagrams
    Management – usually done by leader
The leader can change over the semester if that is what the group wants

## Slide 3: Leadership Styles
Dictator – not desirable
  They come up with all the ideas and unilaterally make all of the assignments and decisions
  Everyone else serves the dictator and does what ever he/she asks
Democracy -- slow
  Ideas can come from anyone
  Decisions and assignments are made by consensus
Benevolent Dictator – often best but should be an egoless dictator
  Listens to all ideas makes final decisions
  Listens to suggestions or volunteers but makes final assignements

## Slide 4: Simple Project Management Tool
The Pert/Gantt Chart
  An example of free software
    http://www.ganttproject.biz/
Concepts
  Work breakdown structure – divide each phase into a set of tasks, each of 1 to a few days duration
  Order the tasks into a directed acyclic graph where the edges represent task dependencies
  Assign start dates, due dates, and expected duration (measured in hours) for each task
    These can be adjusted as needed
  Assign each person or persons to a task
  Identify critical paths

## Slide 5: The Leader
On a frequent basis, monitors progress of all tasks, especially those on the critical path or a path that has just become critical
  Frequent can be every day or every other day
Adjust resources and estimates as necessary

## Slide 6: Expected Weekly Report from Leader
List of All Tasks with assigned people, start dates, expected end dates, expected duration, and actual duration so far
For all finished tasks, mark as finished – color coding is useful
For all unstarted tasks, mark as not started – color coding is useful
For all started but not completed tasks indicate % complete
  The actual duration / expected duration should yield the % complete
Indicate the number of hours worked for every team member, if this does not match the “Pert/Gannt” chart information then add or delete tasks and modify expected and/or actual durations for tasks as needed.
This report should be reviewed by all team members
A final report should be generated for every phase
  The final version is typically the weekly report for the last week of a phase
  The phase is not complete until the final report is turned in
Spread sheets make this somewhat painless