## Sheet1
Phase 1 Report For Week Ending: |  |  | 2016-01-21 | Team Leader: | Minnie Mouse
| Team Member | Task for | Start Date | Expected Ending Date | Actual Ending Date | Hours Worked this Week | Total Hours Worked So Far
Micky Mouse
|  | Create Class Diagram for Design | 2016-01-14 | 2016-01-18 | 2016-01-19 | 6 | 8 | Working with Pluto on same task
|  | Design Devel. Card Class and Specializations | 2016-01-19 | 2016-01-20 |  | 4 | 4 | Unfinished Task on critical path
|  | Javadoc Devel. Card Class and Specializations | 2016-01-25 | 2016-01-27
[5 empty] | Total | 10 | 12
Pluto
|  | Create Class Diagram for Design | 2016-01-14 | 2016-01-18 | 2016-01-19 | 4 | 5 | Working with Micky Mouse on same task
|  | Implement Devel. Card Class | 2016-01-22 | 2016-01-26
|  | Test Devel. Card Class | 2016-01-26 | 2016-01-28
[5 empty] | Total | 4 | 5
Donald Duck
|  | Design Player Class | 2016-01-15 | 2016-01-20 |  | 1 | 2
|  | Implement Player Class | 2016-01-21 | 2016-01-25
[5 empty] | Total | 1 | 2
Means that this task has been completed, whether it was on time or not
Means this task has not been completed
Designates a late, uncompleted task, on the critical path
You can change the color coding in any way that will help your team.
We suggest that the team leader not do this entire report. You might consider having every team member do their section and turn it in as a spreadsheet to the leader.
The team leader then compiles this report (mostly by cut and paste), checks for inconsistancies, and turns it in.